## RACI
RACI Matrix |  | Legend (RACI)
R = Responsible (Person who does the work)
A = Accountable (Person who owns the task/outcome)
C = Consulted (Person who gives input)
| ` | I = Informed (Person who needs to be updated)
|  | Project Sponsor | Product Manager | Release Train Engineer | Systems Architect | Team Product Owner | Team Scrum Master | Technical Mentor | General Team Member | Notes
Open FinAL Product |  | [PROFESSOR NAME] | [MEMBER NAME] | [MEMBER NAME] | [MEMBER NAME]
Deliverable/Tasks
Customer discovery and voice of customer insight |  | A | R | R | R | R | R | R | R | Product Manager leads effort with support of Product Owners. All students involved to develop customer-focused mindset
New idea review and decisions |  | A | R | C | C | C | I | I | I
Develop and maintain strategic roadmaps |  | A | R | C | C | C | I | I | I
Communicate changes with stakeholders |  | A | R | C | C | C | I | I | I
Set budgets and monitor expenditures |  | A | R | C | C | C | I | I | I
Prioritize the epics/features/milestones |  | A | R | C | C | C | I | I | I
Regulatory compliance |  | A | R | C | C | C | I | I | I
Monitor project risk |  | A | C | R | C | C | C | I | I
Monitor and manage the product increment plan |  | I | A | R | C | C | C | I | I
System Demos (end of each sprint) |  | I | C | R | R | C | R | C | C | RTE leads meeting; System Architect describes changes to architecture when needed; Scrum Masters demo team features
Leadership retrospective (end of each sprint) |  | I | C | R | C | C | C | I | I | RTE leads meeting; PM, SA, SM, and POs participate
Project closure |  | A | C | R | C | C | C | I | I
Manage software architecture |  | A | I | I | R | I | I | C | I
Develop and manage testing automations |  | A | I | I | R | I | I | C | I
Develop and manage git/continuous integration practices |  | A | I | I | R | I | I | C | I
Deployment |  | A | C | C | R | C | C | C | C
Prioritize team product backlog |  | I | A | I | I | R | C | C | C
Define sprint goals and prioritize sprint backlog |  | I | A | I | I | R | C | C | C
Assign and monitor sprint backlog tasks |  | I | I | A | I | C | R | C | C
Gather technical requirements for tasks |  | I | I | I | A | C | C | R | R
Conduct daily scrum meetings |  | I | I | A | I | C | R | C | C
Run team retrospective meetings (end of each sprint) |  | I | I | A | I | C | R | C | C
Software development |  | I | I | I | A | I | C | R | R
Software testing |  | I | I | I | A | I | C | R | R
Documentation |  | I | I | A | C | C | R | R | R

## Decision Log
| Team/ Date/ Time | KEY DECISION | ASSOCIATED RISKS | ALTERNATIVES CONSIDERED | RATIONALE FOR DECISION | COST IMPLICATION SHORT LONG TERM TERM | VOTE: TEAM CONSENSUS, PROJECT MANAGER, ADMINISTRATION, PROFFESSOR | PLACE OF RECORD: CLICKUP, CHARTER, VISION, OTHER
Notes: ● Routine project decisions are made by team consensus. ● If consensus cannot be reached, the Product Manager/Team Lead acts as final arbiter after considering input. ● Cross-team or strategic issues are escalated to the instructor or coordinating leads for resolution. ● Major decisions (e.g., scope changes, deliverable revisions) are recorded and reviewed during retrospectives to capture lessons learned. ● This structure supports timely decisions and team autonomy while maintaining an inclusive, data-driven management process.
Administration
Product Owner
Release Train Engineer
Sub-teams
Team Product Owner
Scrum Master
Team Members
Jeff