# Epic: Donor Outreach Kit

Goal: Equip the OpenFinAl team with materials, tools, and processes to identify, approach, and convert potential donors/partners.

## Feature 1 — Target Donor Research

### Outcome

A qualified list of donor prospects with prioritization.

Tasks

- Define ideal donor profile (ICP)

- Identify donor segments (foundations, fintech sponsors, universities)

- Build prospect database (CRM or spreadsheet)

- Gather contact information

- Score and prioritize prospects

- Validate list with stakeholders

## Feature 2 — Outreach Messaging & Positioning

### Outcome

Clear, consistent messaging for donor communication.

Tasks

- Define value proposition for donors

- Draft outreach narrative (mission + impact)

- Create elevator pitch

- Write email outreach templates

- Write LinkedIn message templates

- Create call script

- Internal review & approval

## Feature 3 — Donor Pitch Materials

### Outcome

Professional assets to support outreach.

Tasks

- Create pitch deck

- Design one-pager overview

- Develop impact metrics slide

- Prepare FAQ document

- Build demo script

- Review branding consistency

## Feature 4 — Outreach Execution Process

### Outcome

Repeatable process for contacting donors.

Tasks

- Define outreach workflow (research → contact → follow-up)

- Set cadence for follow-ups

- Configure CRM tracking

- Assign outreach ownership

- Create status tracking dashboard

- Document SOP

## Feature 5 — Measurement & Optimization

### Outcome

Ability to evaluate outreach effectiveness.

Tasks

- Define success metrics (response rate, meetings booked, funding secured)

- Build tracking sheet/dashboard

- Conduct weekly outreach review

- Identify messaging improvements

- Iterate templates

# Example Deliverables for the Epic

- Prospect list

- Messaging playbook

- Pitch deck

- Outreach templates

- Outreach tracking dashboard

# Definition of Done

- Team has ready-to-use outreach materials

- Prospect pipeline exists

- Outreach process documented